## Prototype Plan
Prototype Plan
CUSTOMER |  |  | STELLANTIS | [25 empty] | PART NUMBER | [14 empty] | EP_05_RSG
PART NAME |  |  | Fiat Tris Rear Sliding Glass | [25 empty] | PART REVISION NU / REV.DATE | [14 empty] | 16.09.2026
Nu. | Tasks |  | Plan | Start Prototype Phase = Official PO & Tooling Advance (T0) | [51 empty] | DEPARTMENTS | RELATED PRODUCTS & NECESSITYS
|  |  | Real | WEEKS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
01 | Design Freeze |  | P | [52 empty] | Engineering | CAD Freeze for Prototype | bar: WEEKS 1
R
02 | Aluminum Extrusion Mold And Production |  | P | [52 empty] | Engineering & Purchasing | Frame & Glazing Bar Profiles | bar: WEEKS 2 to WEEKS 6
R
03 | Epdm Rubber Extrusion Mold And Production |  | P | [52 empty] | Engineering & Purchasing | Epdm Rubber & Stopper | bar: WEEKS 2 to WEEKS 6
R
04 | Plastic Injection Mold And Production |  | P | [52 empty] | Engineering & Purchasing | Handle & Lock Keeper | bar: WEEKS 2 to WEEKS 5
R
05 | Control Fixtures |  | P | [52 empty] | Engineering & Purchasing | Product Quality | bar: WEEKS 2 to WEEKS 7
R
06 | Aluminum Profile Bending Dies |  | P | [52 empty] | Purchasing | Main Shape | bar: WEEKS 2 to WEEKS 7
R
07 | Sub-Parts Purchasing |  | P | [52 empty] | Purchasing | Bolts | bar: WEEKS 2
R
08 | Glass Production |  | P | [52 empty] | Production | Fixed & Sliding Glasses | bar: WEEKS 6 to WEEKS 7
R
09 | First OT |  | P | [52 empty] | Production | Aluminum Frame | bar: WEEKS 7 to WEEKS 8
R
10 | Prototype Control Plan |  | P | [52 empty] | Quality | Prototype | bar: WEEKS 7
R
11 | Customer Sample Approval |  | P | [52 empty] | Customer | Prototype | bar: WEEKS 9 to WEEKS 10
R
12 | Laboratory Tests |  | P | [52 empty] | Engineering & Purchasing | Guarantee Product Standarts | bar: WEEKS 11 to WEEKS 14
R
13 | Product Presentation & Final Reports |  | P | [52 empty] | Project Team | Prototype Phase Closure | bar: WEEKS 15
R
TRIS proje planı: renkli plan işaretleri hedefi gösterir; gerçekleşme ve müşteri onayı kanıtla tamamlanır.

## Mass Production Plan
Mass Production Plan
CUSTOMER |  |  | STELLANTIS | [25 empty] | PART NUMBER | [14 empty] | EP_05_RSG
PART NAME |  |  | Fiat Tris Rear Sliding Glass | [25 empty] | PART REVISION NU / REV.DATE | [14 empty] | 2026-09-16
Nu. | Tasks |  | Plan | RELATIVE DATE (AFTER START MASS PRODUCTION PHASE) | [51 empty] | DEPARTMENTS
|  |  | Real | WEEKS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
01 | Line Setup Validation |  | P | [52 empty] | Production & Engineering | bar: WEEKS 4 to WEEKS 5
R
02 | Pre-launch & Production Control Plan |  | P | [52 empty] | Quality | bar: WEEKS 1
R
03 | Process Failure Mode and Effects Analysis (PFMEA) |  | P | [52 empty] | Quality | bar: WEEKS 3 to WEEKS 5
R
04 | Measurement Systems Analysis (MSA) |  | P | [52 empty] | Quality | bar: WEEKS 1
R
05 | Packaging & Logistics Standard Approval |  | P | [52 empty] | Quality | bar: WEEKS 2
R
06 | OTOP (Off-Tool Off-Process) Trial Run |  | P | [52 empty] | Production & Quality | bar: WEEKS 6
R
07 | Preliminary Process Capability Study (Cpk / Ppk) |  | P | [52 empty] | Quality | bar: WEEKS 1
R
08 | Product Validation (PV) Tests |  | P | [52 empty] | Quality | bar: WEEKS 7
R
09 | PPAP Documentation & Submission (PSW) |  | P | [52 empty] | Project Team | bar: WEEKS 1
R
10 | Customer Approval & SOP (Start of Production) |  | P | [52 empty] | Project Team & Production | bar: WEEKS 9
R